## MCP tool list
Test-id | Description | Expected result | Obtained result | Status | Tester Observations | Programmer Observations
TASK040-1 | tools/list over stdio returns the full tool set | Seven tools: the three maintenance ones, then route, gate_reports, verdict, human_queue | Drove dist/mcp/server.js: all seven returned, maintenance first | OK |  | Verified against the built binary, not just the unit test
TASK040-2 | The pinned exact-equality assertions still pin | tests/mcp/tools.test.ts and tests/mcp/server.test.ts both assert the full seven names with toEqual | Both extended to seven and kept exact; no toContain, no length check | OK |  | Loosening either was the failure mode this row exists to catch
TASK040-3 | No tool exposes gate or govern | No tool name runs a gate stage or a governance pass | Asserted in tools.test.ts; the carve-out is recorded in code, neuron, README and plan | OK |  | The deliberate GAP A decision
TASK040-4 | initialize reports the shipped version | serverInfo.version matches package.json | serverInfo -> {"name":"ql-pipeline","version":"0.2.0"} | OK |  | server.ts hardcodes it, so the bump had to move both
TASK040-5 | Every tool name is unique | No inspection tool collides with a maintenance tool | Asserted over TOOLS in tools.test.ts | OK
TASK040-6 | An unknown tool name is still an error result, not a throw | runTool answers isError with a message rather than rejecting | Existing assertion still passes; inspection dispatch falls through on an unknown name | OK |  | runInspectTool answers null for anything it does not own
TASK040-7 | The JSON-RPC stream stays clean with the engine imported | No non-JSON line reaches stdout once the server imports the governance engine | 6 of 6 responses parsed; no protocol corruption, stderr empty | OK |  | The real risk of moving from spawn-only to in-process; checked explicitly

## Run inspection
Test-id | Description | Expected result | Obtained result | Status | Tester Observations | Programmer Observations
TASK040-8 | ql_pipeline_route reports areas, rules and gates | A feat(infrastructure) commit routes to infrastructure with its two rule files and both gate commands | Returned infrastructure, _common.rules + infrastructure.rules, and this repo's real gate commands | OK |  | Run against ql-pipeline itself via the built server
TASK040-9 | The config probe finds a root-level pipeline.config.yml | A repo that keeps its config at the root, not under .github/, still resolves | Resolved F:\Projects\ql-pipeline-wt-mcp\pipeline.config.yml | OK |  | createPipelineContext only knows the .github path; an inspector needs both
TASK040-10 | An unroutable PR is an answer, not a failure | isError stays false and the payload carries routable:false plus the reason | Matches; the reason is the engine's own wording | OK |  | isError would tell an agent the tool broke
TASK040-11 | A repo with no pipeline config is reported, not thrown | An error result naming what was looked for | "no pipeline config found ..." with both candidate paths | OK
TASK040-12 | A malformed config surfaces as an error result | ConfigError's message reaches the caller instead of the JSON-RPC layer | Error result carrying the config validation message | OK
TASK040-13 | ql_pipeline_gate_reports reports what the gate jobs left | Per area and stage: command, passed, output | Returned the injected outcome verbatim | OK
TASK040-14 | A missing reports directory says so | Empty outcomes plus a note, rather than a bare empty list | note: "no gate reports found ..." | OK |  | Confirmed against the real repo, which has no gate-reports dir
TASK040-15 | An unreadable gate report fails closed | The pipeline's own fail-closed reason is passed through as an error | "could not read gate report ..." surfaced unchanged | OK |  | Uses govern's readGateReports rather than a private re-walk
TASK040-16 | ql_pipeline_verdict reaches MERGE when nothing blocks | verdict MERGE, no blocking findings | Matches | OK
TASK040-17 | A failed required gate becomes a blocking finding and a FIX | verdict FIX with one gate-derived finding | Matches; findingsFromGates = 1 | OK |  | Same path govern takes: a build break is just another finding
TASK040-18 | A non-auto-fixable finding BLOCKs | verdict BLOCK with the engine's reason | "one or more findings require a human (not auto-fixable)" | OK |  | Also confirmed end to end through the built server
TASK040-19 | Exhausted fix attempts BLOCK | Three [bot] commits with maxFixAttempts 3 gives BLOCK | attemptsSoFar 3, reason "max fix attempts (3) reached" | OK |  | Attempts counted from commit messages by countFixAttempts
TASK040-20 | Advisory and blocking findings stay separate | A should-severity finding is advisory; a security one blocks | One in each bucket | OK
TASK040-21 | A finding with an unknown severity is refused | Error result naming the allowed severities, no verdict produced | "findings[0].severity must be one of must, should, security" | OK |  | Coercing it would silently change the verdict
TASK040-22 | A finding missing autoFixable is refused | Error result rather than defaulting the flag | "findings[0].autoFixable must be a boolean" | OK |  | autoFixable decides FIX vs BLOCK
TASK040-23 | findings must be an array | A non-array is refused with a clear message | "\"findings\" must be an array" | OK

## Human queue
Test-id | Description | Expected result | Obtained result | Status | Tester Observations | Programmer Observations
TASK040-24 | ql_pipeline_human_queue reads both queues by default | needs-human and ready-to-merge, in that order, each with its count | Both queried with the exact label constants from merger.ts | OK |  | Labels imported, never re-spelled as literals
TASK040-25 | A single queue can be asked for | queue: ready-to-merge queries one label only | One call, one queue in the payload | OK
TASK040-26 | It writes nothing | No label, comment, approval, push, merge or thread resolution is called | Asserted against a full client of spies; every writing method untouched | OK |  | The promise the whole module makes; a regression here is the one that matters
TASK040-27 | A missing GITHUB_TOKEN is reported, not thrown | An error result naming the variable | Confirmed through the built server with GITHUB_TOKEN empty | OK
TASK040-28 | owner and repo are required | An error result when either is missing | "\"owner\" and \"repo\" are both required" | OK
TASK040-29 | An unknown queue name is refused | Error result listing the valid values | "\"queue\" must be one of needs-human, ready-to-merge, both" | OK
TASK040-30 | A GitHub failure becomes an error result | A rejected API call is caught and reported | "could not read the human queue ...: Bad credentials" | OK |  | Never escapes to the JSON-RPC transport
TASK040-31 | Issues carrying the label are excluded | Only entries with a pull_request member are listed | Filtered in listPullRequestsByLabel | OK |  | Issues and pull requests share GitHub's label API

## Repo gate and harness
Test-id | Description | Expected result | Obtained result | Status | Tester Observations | Programmer Observations
TASK040-32 | pnpm typecheck | Exit 0 | Exit 0 | OK
TASK040-33 | pnpm lint | Exit 0 | Exit 0 | OK
TASK040-34 | pnpm test | Green, with more tests than the 640 baseline | 51 files, 670 tests, exit 0 (baseline 50 / 640) | OK |  | 30 new tests
TASK040-35 | pnpm neurons | Every @signal has a documented entry | "OK: every @signal has a documented entry" | OK |  | The new unit's neuron ships in the same commit
TASK040-36 | ql-docs validate-harness.py adds no error | The branch's findings match main's exactly | 23 pre-existing errors on both; zero added, zero removed | OK |  | main's raw count is inflated by a nested .claude/worktrees copy
TASK040-37 | Committed dist is rebuilt | dist carries the new tools, since the package ships dist | pnpm build run; dist/mcp/inspect.js added, tools/server/github-client updated | OK |  | Task 011 committed dist on purpose; a stale one would ship three tools