## MCP Cases
Case-id | Feature area | Precondition | Call | Input | Expected result | Severity | Obtained result | Status

## Preview job
Test-id | Description | Expected result | Obtained result | Status | Tester Observations | Programmer Observations
TASK052-1 | previewUpArgs carries --no-announce after the lifetime, and still carries --pr | up --branch … --pr 42 --dir … --ttl 120 --no-announce --protect | Exact match | OK | --pr stays for teardown by repo+pr
TASK052-2 | deployPreview spawns ql-proxy with no GitHub token in the child environment | env has QL_TASK_FOLDER, QL_MCP_ENABLED, QL_PROXY_CONFIG and no GH_TOKEN | As expected | OK
TASK052-3 | The deploy command exports no ANNOUNCE_TOKEN_VAR | Symbol gone; typecheck green | Gone | OK
TASK052-4 | The workflow's preview job sets no QL_PREVIEW_ANNOUNCE_TOKEN | grep finds nothing | Nothing | OK
TASK052-5 | The full suite, typecheck, lint and neuron check stay green | All green | 858 tests, 60 files; typecheck, lint, neurons green | OK | One argv case added
TASK052-6 | The harness validator matches the 050 head this stacks on | Identical | Identical, 24 pre-existing errors on both | OK | Diffed against the 050 head (20db282)
TASK052-7 | Live: a preview gets exactly one comment, the pipeline's summary | One comment |  |  | Gate 3 — needs a product repo, a runner, and ql-proxy 0.2.0 on the host